## Project Planner
End-to-End Document Layout Analysis using Deep Learning for the DocBank Dataset - Project Planner
Legends : |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Topic selection | 1 | 2 | 1 | 2 | 100%
Literature review | 3 | 4 | 3 | 4 | 100%
Feasibility study | 7 | 1 | 7 | 1 | 100%
H/W & S/W requirements | 8 | 1 | 8 | 1 | 100%
M1 - Research Proposal | 1 | 8 | 1 | 8 | 100%
Detailed literature review | 9 | 4 | 0 | 0 | 0%
Proposed method | 13 | 2 | 0 | 0 | 0%
Detailed architecture | 19 | 4 | 0 | 0 | 0%
Feedback | 23 | 2 | 0 | 0 | 0%
M2 - Interim report | 9 | 12 | 0 | 0 | 0%
Experimental set up | 25 | 3 | 0 | 0 | 0%
Coding | 28 | 6 | 0 | 0 | 0%
Model building and inference | 32 | 5 | 0 | 0 | 0%
Model evaluation | 37 | 3 | 0 | 0 | 0%
Result analysis and conclusions | 40 | 2 | 0 | 0 | 0%
Feedback | 42 | 1 | 0 | 0 | 0%
M4 - Final report | 25 | 20 | 0 | 0 | 0%
Slide preparation | 43 | 1 | 0 | 0 | 0%
Video presentation | 44 | 1 | 0 | 0 | 0%
M5 - Presentation | 43 | 2 | 0 | 0 | 0%
TOTAL |  | 42